## RACI Platform Ownership
RACI Matrix for Platform Ownership - Power BI
|  |  | Platform Core Team | [18 empty] | Key Stakeholders
|  |  | Barbara Stallings | Prod | Non-Prod | Prod | Non-Prod | Prod | Non-Prod | Prod | Non-Prod | Prod | Non-Prod | Prod | Non-Prod | Prod | Non-Prod | Prod | Non-Prod | Prod | Non-Prod
|  |  |  | Vikas Sanikommu | N/A | Varies | Varies | Varies | Varies | Varies | Varies | N/A | TBD | Varies | Varies | Pavan Reka | Pavan Reka | Barb Stallings | Patty Allen | Barb Stallings | Patty Allen | Dave Jones | Varies
| M/O/C | Description | Platform Owner | ESS Platform Support |  | Network Storage |  | DSA |  | WIS |  | GTS Engineering |  | Ent. Security |  | GBS Architecture |  | Vendor Manager |  | Project Manager |  | Business Partner | Compliance & Risk
Support | M | ▪Platform Monitoring / High Availability ▪ Level 2 & 3 support ▪ Problem Coordination ▪ Crit Sit Management ▪ Management Escalation ▪ Upgrades and patches: ▪ Documentation and testing ▪ Planning ▪ Management, execution ▪ Metrics collection and reporting ▪ Disaster Recovery testing ▪ Review, renew and fund annual maintenance contract | A | R | C/I | C | C | C | C | C | C | C | R | C | C | C | C | C | C | R (Upgrades, Patches, Testing) | R (Upgrades, Patches, Testing) | I | I
Infrastructure | C | ▪ Performance/performance testing ▪ Scalability ▪ High Availability ▪ Hardware (compute, storage, network): Monitoring, upgrade/Replace, Tuning ▪ Database monitoring, repository database storage, upgrades, patches, backup, recovery, tuning ▪ OS: Monitoring ▪ OS: Patch/Upgrade, ▪ Disaster recovery | A | C | C/I | R | R | R | R | R | R | C | R | N/A | N/A | I | I | I | I | C | C | I | I
Standards & Governance | M | ▪ Define and Enforce Standards and Best Practices ▪ Guidance on appropriate usage ▪ Compliance & Audit Consideration ▪ Platform Architecture (security below) ▪ Developer education and support ▪ Developer tooling | A | C | C/I | N/A | N/A | C | C | C | C | R | R | N/A | N/A | C | C | C | C | C | C | I | C
Metadata Build | C | ▪ Build and maintain metadata layer for project teams ▪ Semantic level mapping to new and existing databases ▪ Resolve data quality issues | O | C | C | C | C | N/A | N/A | N/A | N/A | I | C | N/A | N/A | R | R | N/A | N/A | I | I
Strategy | M | ▪ Product Roadmap ▪ Portfolio Rating - Buy, Sell, Hold ▪ Sector and competitor analysis ▪ Stay current on technology trends, business opportunities and impacts ▪ Proactive review and communication of upcoming features | A | C | C | N/A | N/A | I | I | N/A | N/A | C | R | N/A | N/A | C | C | R | R | C |  | C | I
Security | M | ▪ Define security requirements and secure architecture ▪ Define security model ▪ Manage platform access and role creation | A | R | C | C | C | R | R | R | R | I | R | C | C | R/C | R/C | C | C | C | C | I | I
|  | ▪ New Folders, App Security, and Connection set-up ▪ Maintain Windows AD groups and Security Access form ▪Troubleshoot User Access rights ▪Vulnerability identification | A | R | C | C | C | R | R | C | C | I | R | R | R | R/C | R/C | C | C | C | C | I | I
Platform Admin | M | ▪ Project Onboarding (new folders, connection setups) ▪Product Configuration ▪Assign roles and permissions ▪Infrastructure Integration | A | C | C | C | C | C | C | C | C | I | R | C | C | C | C | C | C | C | C | I
Vendor Mgt | M | ▪ Primary vendor POC ▪ License Compliance ▪ Contract Negotiation ▪ Account Management meetings ▪ Vendor Questionnaire | A | C | N/A | N/A | N/A | C | C | N/A | N/A | C | C | N/A | N/A | N/A | N/A | R | R | C | C
Oversight | M | ▪ Coordination across all components ▪ Communication with all stakeholders ▪ Escalate issues as needed ▪ Advocacy and education ▪ Problem trend analysis and reporting ▪ Platform Scorecard ▪ Infrastructure/platform SLA Creation ▪ Funding/Chargeback | A/R | R | N/A | N/A | N/A | C | C | C | C | C | C | N/A | N/A | C | C | C | C | C | C | I
Engineering | M | ▪ Coordination across all components ▪ Communication with all stakeholders ▪ Escalate issues as needed ▪ Advocacy and education ▪ Problem trend analysis and reporting ▪ Platform Scorecard ▪ Infrastructure/platform SLA Creation ▪ Funding/Chargeback | A/R | R | N/A | N/A | N/A | C | C | C | C | C | C | N/A | N/A | C | C | C | C | C | C | I
C - Consulted - Possess the information and/or capability to complete work. Two way communication with R. Optional
I - Informed - One way communication of progress and results. Optional
R - Responsible - Completes the work. There should be at least one R and there can be multiple Rs (R most Platforms, r some platforms)
A - Accountable - Approves the completed work and is ultimately answerable. There should be one and only one A